FIWARE-based MRP Proof of Concept

GitHub Workplan and Step-by-Step Tutorial Guide

Twelve-week plan to build an executable reference implementation from an empty repository

| Field | Value |
| --- | --- |
| Document version | Draft v0.1 |
| Date | 2026-06-18 |
| Audience | Architecture board, product owner, FIWARE developers, industrial adopters |
| Scope | Reference implementation and tutorial-driven PoC for an MRP module on NGSI-LD |
| Data model policy | Project-owned models only; structurally compatible with Smart Data Models conventions |

# Document map

| Section | Purpose |
| --- | --- |
| 1. Delivery model | How the workplan is organized and how every week remains executable. |
| 2. Repository bootstrap | Commands and files to create the reference implementation repository. |
| 3. Engineering standards | Branching, releases, code style, test strategy and CI/CD. |
| 4. Tutorial authoring standard | Template for FIWARE-style step-by-step tutorials. |
| 5. Twelve-week implementation plan | Weekly goals, tasks, files, tutorial steps and acceptance criteria. |
| 6. Final release checklist | How to publish the PoC as a coherent reusable reference implementation. |

# 1. Delivery model

The repository must evolve as a series of executable increments. Each weekly tag must start with Docker Compose, seed data, execute a demo script, and pass automated tests. The workplan intentionally mirrors FIWARE Step-by-Step tutorials: each tutorial introduces a limited set of concepts, uses cURL or HTTP requests, shows the flow of context data, and ends with validation commands.

Every week is a working PoC, not only a design increment.

The default reader should be able to run the tutorial locally without knowing the previous development history.

The tutorial and the code are delivered in the same pull request.

Tutorial scripts must be deterministic: reset, seed, execute, assert and stop.

Business logic is implemented through command APIs, while the tutorial also exposes the resulting NGSI-LD context.

# 2. Repository bootstrap from zero

## 2.1 Initial GitHub creation

# Option A: GitHub CLI

gh repo create arise-fiware-mrp-reference --public --description "FIWARE-based MRP reference implementation and step-by-step tutorials"

git clone https://github.com/<org>/arise-fiware-mrp-reference.git

cd arise-fiware-mrp-reference

# Option B: manual GitHub creation

mkdir arise-fiware-mrp-reference

cd arise-fiware-mrp-reference

git init

git remote add origin git@github.com:<org>/arise-fiware-mrp-reference.git

## 2.2 First commit structure

mkdir -p .github/workflows .github/ISSUE_TEMPLATE

mkdir -p contexts/mrp/v0.1 data-models/dataModel.MRP

mkdir -p services/{context-server,mrp-api,bom-service,inventory-service,scheduler-service,shopfloor-service}

mkdir -p tutorials/01-getting-started-context/{seed,expected,tests}

mkdir -p scripts postman docs/architecture docs/adopters

touch README.md LICENSE.md CONTRIBUTING.md CODE_OF_CONDUCT.md SECURITY.md

touch docker-compose.yml Makefile .env.example .gitignore

git add .

git commit -m "chore: bootstrap FIWARE MRP reference repository"

git push -u origin main

## 2.3 Target repository tree

arise-fiware-mrp-reference/

README.md

LICENSE.md

CONTRIBUTING.md

SECURITY.md

Makefile

docker-compose.yml

.env.example

contexts/

mrp/v0.1/context.jsonld

mrp/latest/context.jsonld

data-models/

dataModel.MRP/<ModelName>/{README.md,schema.json,doc/spec.md,examples/...}

services/

context-server/

mrp-api/

bom-service/

inventory-service/

scheduler-service/

shopfloor-service/

quality-service/

mps-service/

iot-simulator/

tutorials/

01-getting-started-context/

02-inventory/

...

12-end-to-end-demo/

scripts/

reset.sh

seed.sh

test.sh

wait-for-orion.sh

postman/

FIWARE-MRP.postman_collection.json

docs/

architecture/

adopters/

# 3. Engineering standards

## 3.1 Branching and releases

| Rule | Specification |
| --- | --- |
| Default branch | main must always run the latest complete tutorial and all previous tests. |
| Feature branches | feature/tutorial-XX-short-name or feature/service-name-capability. |
| Weekly release tags | v0.1 through v0.12. Tag only after demo and tests run from clean checkout. |
| Pull requests | One PR per tutorial increment. Include code, data models, scripts, documentation and tests. |
| Versioned contexts | contexts/mrp/v0.X/context.jsonld is immutable after release; latest may point to current development version. |
| Model versioning | Each model README and schema includes modelVersion. Backward incompatible changes require migration notes. |

## 3.2 Toolchain

| Tool | Purpose |
| --- | --- |
| Docker Compose | Local multi-container runtime for Orion-LD, MongoDB and services. |
| Orion-LD | NGSI-LD Context Broker. |
| Node.js or Python service runtime | Implement tutorial services and command APIs. Select one runtime for consistency. |
| OpenAPI | Business API contract documentation. |
| JSON Schema | Model validation and data model compatibility. |
| Hurl/Newman/pytest | HTTP-based integration tests and tutorial assertions. |
| GitHub Actions | CI checks, Docker build, test execution and documentation linting. |
| Markdown lint and shellcheck | Quality gates for tutorials and scripts. |

## 3.3 Standard Makefile targets

make start          # start the stack

make stop           # stop containers

make reset          # stop and remove volumes for deterministic state

make seed           # load baseline tutorial data

make demo-01        # execute tutorial 01 demo

make test-01        # run tutorial 01 assertions

make test-all       # run all tutorial tests up to current tag

make logs           # follow service logs

make lint           # lint docs, schemas and scripts

make package        # create distributable tutorial bundle

## 3.4 CI workflow baseline

name: ci

on:

pull_request:

push:

branches: [ main ]

jobs:

test:

runs-on: ubuntu-latest

steps:

- uses: actions/checkout@v4

- name: Validate JSON schemas

run: make lint-schemas

- name: Start stack

run: make start

- name: Wait for Orion-LD

run: ./scripts/wait-for-orion.sh

- name: Seed data

run: make seed

- name: Run tutorial tests

run: make test-all

- name: Dump logs on failure

if: failure()

run: make logs-ci

- name: Stop stack

if: always()

run: make stop

# 4. Tutorial authoring standard

Each tutorial directory must be understandable and executable on its own. The style should be hands-on and API driven.

| Section | Required content |
| --- | --- |
| Objective | One business capability and one learning outcome. |
| Architecture | Components used in this tutorial and what was added since the previous tutorial. |
| Models introduced | Entity types, attributes and relationships introduced or changed. |
| Start services | Exact make/docker commands. |
| Seed data | Exact seed command and expected entities. |
| Exercises | Numbered cURL/HTTP requests with expected responses. |
| Context inspection | NGSI-LD queries that prove the business effect. |
| Tests | Command to run automated test and expected pass criteria. |
| Cleanup | Reset command. |
| Next tutorial | One paragraph connecting to the following increment. |

## 4.1 Tutorial README template

# Tutorial XX - <Business capability>

## What you will build

## Architecture of this tutorial

## Models introduced

## Prerequisites

## Start the stack

## Load seed data

## Exercise 1 - <action>

## Exercise 2 - <action>

## Inspect the resulting NGSI-LD context

## Automated tests

## Troubleshooting

## Clean up

## What comes next

## 4.2 Definition of Done for each week

Clean checkout can run make start, make seed, make demo-XX and make test-XX.

All previous tutorial tests still pass.

Every new model has schema.json, spec.md, README.md and NGSI-LD examples.

Every new command endpoint appears in the OpenAPI contract and in tutorial requests.

The README contains expected outputs or assertions, not only commands.

A release tag v0.X exists after merge to main.

At least one business value statement is demonstrated by an NGSI-LD query.

# 5. Twelve-week implementation plan

## Week 1 - Tutorial 01: Getting started with the FIWARE MRP context

| Item | Detail |
| --- | --- |
| Business value | A runnable FIWARE stack with a project-owned @context and a minimal factory graph. |
| Models | Company, Plant, ProductionLine, WorkCenter, Product, StockLocation |
| Services | context-server, seed-loader, minimal mrp-api health endpoint |

### Implementation tasks

Create docker-compose.yml with Orion-LD, MongoDB, context-server and mrp-api.

Create contexts/mrp/v0.1/context.jsonld.

Create first six data model folders with schema/spec/examples.

Implement seed script for sample factory, work centers, products and locations.

Write Tutorial 01 with cURL commands and context queries.

Add health check and test that counts entities by type.

### Tutorial steps

1. Clone repository and run make start.

2. GET Orion-LD version and context-server context URL.

3. Run make seed.

4. Query Products, Plant and WorkCenters through NGSI-LD.

5. Inspect relationships Plant -> WorkCenter and WorkCenter -> StockLocation.

6. Run make test-01.

Acceptance criterion: Clean checkout returns 1 Plant, 3 WorkCenters, 5 Products and 2 StockLocations through NGSI-LD.

## Week 2 - Tutorial 02: Inventory balances and material receipts

| Item | Detail |
| --- | --- |
| Business value | The PoC answers what stock is available by product, location and lot. |
| Models | InventoryBalance, StockMove, Lot |
| Services | inventory-service v0, validation-service v0 |

### Implementation tasks

Implement receive-material command endpoint.

Create receipt StockMove and update InventoryBalance.

Add lot tracking examples.

Implement JSON Schema validation for Product, Location and InventoryBalance payloads.

Write tutorial queries for stock by product, location and lot.

Add negative test for non-existent product.

### Tutorial steps

1. Start and seed Week 1 baseline.

2. POST receive-material for PumpCasing, Impeller, ElectricMotor, SealKit and ScrewSet.

3. Query InventoryBalance with options=keyValues.

4. Query by lot and by location.

5. Send invalid receipt and inspect Problem Details response.

6. Run make test-02.

Acceptance criterion: InventoryBalance.availableQuantity equals quantityOnHand minus reservedQuantity for each component.

## Week 3 - Tutorial 03: Bill of Materials and BoM explosion

| Item | Detail |
| --- | --- |
| Business value | The PoC calculates gross component requirements for any manufacturing quantity. |
| Models | BillOfMaterials, BillOfMaterialsLine, RoutingOperation, MaterialRequirement |
| Services | bom-service v0 |

### Implementation tasks

Create BoM models and examples.

Implement POST /boms/{id}/explode.

Generate MaterialRequirement entities without yet creating a ManufacturingOrder.

Add routing operations Assembly, LeakTest and Packaging.

Write tutorial that explodes BoM for quantities 10 and 25.

Add tests for component scaling.

### Tutorial steps

1. Create BoM HP100-BOM-v1.

2. Create BoM lines for five components.

3. Create routing operations and dependencies.

4. Run explode command for quantity 10.

5. Query MaterialRequirement entities.

6. Repeat with quantity 25 and compare results.

Acceptance criterion: For 10 finished units, requirements are 10 casing, 10 impeller, 10 motor, 10 seal kit and 80 screws.

## Week 4 - Tutorial 04: Manufacturing order confirmation

| Item | Detail |
| --- | --- |
| Business value | The first real MRP transaction: draft MO to confirmed MO with derived stock moves. |
| Models | ManufacturingOrder, StockMove extensions, MaterialRequirement extensions |
| Services | manufacturing-order-orchestrator v0, bom-service v1 |

### Implementation tasks

Implement create ManufacturingOrder command.

Implement confirmManufacturingOrder command.

On confirmation, call BoM explosion and generate raw and finished StockMoves.

Create state machine guard for draft -> confirmed.

Write tutorial and tests for MO-0001.

Add cancellation path for a draft MO.

### Tutorial steps

1. POST ManufacturingOrder MO-0001 for 10 HydraulicPump-P100.

2. GET MO in draft state.

3. POST confirm command.

4. Query generated MaterialRequirements.

5. Query 5 raw StockMoves and 1 finished StockMove.

6. Cancel MO-TEST and verify final state.

Acceptance criterion: MO-0001 moves from draft to confirmed, with all derived requirements and moves available in the broker.

## Week 5 - Tutorial 05: Component reservations and shortages

| Item | Detail |
| --- | --- |
| Business value | The PoC determines whether an MO can be built with current stock and creates shortages. |
| Models | InventoryReservation, ProcurementRequest |
| Services | inventory-service v1, procurement-service v0 |

### Implementation tasks

Implement reserve-components command.

Calculate available stock and create full or partial reservations.

Create ProcurementRequest when shortage remains.

Update MO reservationState and componentsAvailabilityState.

Add subscription or explicit retry when stock changes.

Write tutorial with sufficient and insufficient stock cases.

### Tutorial steps

1. Create MO-0002 for 10 units and reserve components.

2. Verify MO ready with full reservations.

3. Create MO-0003 for 50 units and reserve components.

4. Verify partial reservation and ProcurementRequest for shortage.

5. Receive missing material and retry reservation.

6. Verify MO-0003 becomes ready.

Acceptance criterion: Stock-sufficient MO becomes ready; stock-insufficient MO becomes waitingComponents and creates ProcurementRequest.

## Week 6 - Tutorial 06: Work orders and finite-capacity-lite scheduling

| Item | Detail |
| --- | --- |
| Business value | The PoC plans manufacturing operations in work centers using routing dependencies. |
| Models | WorkOrder, WorkCenterCalendar, CapacitySlot |
| Services | scheduler-service v0, orchestrator v1 |

### Implementation tasks

Generate WorkOrders from RoutingOperation when MO is confirmed or ready.

Implement scheduleWorkOrders command.

Support operation dependencies: LeakTest waits for Assembly, Packaging waits for LeakTest.

Assign scheduledStart and scheduledEnd based on expectedDuration and work-center capacity.

Support alternative work-center placeholder.

Write tutorial queries for work-center load.

### Tutorial steps

1. Confirm a ready MO with routing.

2. Run scheduling command.

3. Query WorkOrders by ManufacturingOrder.

4. Verify first operation ready and later operations waiting.

5. Query WorkCenter schedule horizon.

6. Run make test-06.

Acceptance criterion: Each ready MO has three scheduled WorkOrders with dependency-consistent states.

## Week 7 - Tutorial 07: Shop-floor execution

| Item | Detail |
| --- | --- |
| Business value | Operators can start, pause, resume, consume material and finish work orders. |
| Models | ProductionEvent, Operator, OperatorAssignment |
| Services | shopfloor-service v0, inventory-service v2, scheduler-service v1 |

### Implementation tasks

Implement start, pause, resume and finish WorkOrder commands.

Implement consume-material command linked to raw StockMove.

Create ProductionEvent for each operator action.

Unlock dependent WorkOrder when predecessor is done.

Add timerStatus and actualStart/actualEnd handling.

Write tutorial with one complete Assembly operation.

### Tutorial steps

1. Create Operator OP-001.

2. Assign OP-001 to Assembly WorkOrder.

3. Start WorkOrder and query inProgress state.

4. Consume components and verify StockMove.doneQuantity.

5. Pause and resume.

6. Finish Assembly and verify LeakTest is ready.

Acceptance criterion: Assembly WorkOrder is done, component inventory decreases, and next WorkOrder is unlocked.

## Week 8 - Tutorial 08: Finished goods, lots and traceability

| Item | Detail |
| --- | --- |
| Business value | The PoC closes an MO and traces produced lot to consumed component lots. |
| Models | ProductionTraceabilityRecord, FinishedGoodsReceipt, ManufacturingCostRecord v0 |
| Services | traceability-service v0, costing-service v0, orchestrator v2 |

### Implementation tasks

Implement receive-finished-goods command.

Move MO to toClose when all WorkOrders are done.

Increment finished goods InventoryBalance.

Create genealogy records from consumed StockMoveLines to produced Lot.

Calculate simple actual cost from material and machine time.

Write tutorial for backward and forward lot traceability.

### Tutorial steps

1. Complete all WorkOrders for MO-0001.

2. Verify MO state toClose.

3. Create produced lot HP100-L001.

4. Receive finished goods.

5. Query InventoryBalance for finished product.

6. Trace HP100-L001 backward to component lots.

Acceptance criterion: MO is done, finished stock increases, and genealogy exists from component lots to finished lot.

## Week 9 - Tutorial 09: Quality, scrap, rework and backorders

| Item | Detail |
| --- | --- |
| Business value | The PoC handles non-ideal production outcomes in a controlled way. |
| Models | QualityCheck, QualityAlert, ScrapEvent, Backorder, ReworkOrder |
| Services | quality-service v0, exception-service v0, inventory-service v3, orchestrator v3 |

### Implementation tasks

Implement quality check result command.

Create QualityAlert on failed check.

Block related WorkOrder, ManufacturingOrder or Lot.

Implement scrap command that creates ScrapEvent and scrap StockMove.

Implement create-backorder for partial production.

Write tutorial for failed LeakTest and partial recovery.

### Tutorial steps

1. Create QualityCheck for LeakTest.

2. Record failed result.

3. Verify QualityAlert and blocked MO/WO.

4. Register scrap for two units.

5. Create rework or backorder for remaining quantity.

6. Close original MO partially and query related backorder.

Acceptance criterion: A quality failure blocks execution, scrap is recorded, and remaining demand is captured as rework or backorder.

## Week 10 - Tutorial 10: MPS-lite planning

| Item | Detail |
| --- | --- |
| Business value | Forecasts and stock are converted into suggested manufacturing orders. |
| Models | DemandForecast, MasterProductionScheduleLine, ReorderingRule |
| Services | mps-service v0, procurement-service v1, orchestrator v4 |

### Implementation tasks

Implement DemandForecast seed and API.

Implement ReorderingRule and projected inventory calculation.

Generate MasterProductionScheduleLine with suggestedProductionQuantity.

Implement convert-to-mo command.

Write tutorial for weekly demand and safety stock.

Add test that suggested quantity respects lot size.

### Tutorial steps

1. Load weekly demand forecast for HydraulicPump-P100.

2. Create ReorderingRule with safetyStock and lotSize.

3. Run MPS calculation.

4. Query MPS line and suggested production.

5. Convert suggestion to ManufacturingOrder.

6. Confirm the generated ManufacturingOrder.

Acceptance criterion: MPS generates a suggested production quantity and creates an executable ManufacturingOrder.

## Week 11 - Tutorial 11: IoT/MES signals, subscriptions and temporal data

| Item | Detail |
| --- | --- |
| Business value | Machine events change work-center availability and trigger maintenance/rescheduling. |
| Models | MachineSignal, MachineState, MaintenanceRequest, TemporalObservation |
| Services | iot-simulator, subscription-listener, maintenance-service v0, scheduler-service v2, temporal-history-service v0 |

### Implementation tasks

Implement IoT simulator that posts MachineSignal.

Create subscription for machineDown events.

Implement MachineState update and MaintenanceRequest creation.

Mark WorkCenter unavailable and trigger reschedule.

Add optional temporal store/Mintaka profile or simple history service.

Write tutorial for downtime and recovery.

### Tutorial steps

1. Start iot-simulator.

2. Create Machine linked to TestBench WorkCenter.

3. Create NGSI-LD subscription.

4. Publish normal signal, then machineDown signal.

5. Verify MaintenanceRequest and WorkCenter unavailable.

6. Replan affected WorkOrders and query history.

Acceptance criterion: A machineDown signal creates maintenance context and reschedules or blocks affected WorkOrders.

## Week 12 - Tutorial 12: End-to-end demo, hardening and publication

| Item | Detail |
| --- | --- |
| Business value | The reference implementation demonstrates forecast-to-finished-goods and is ready for adopters. |
| Models | All models frozen at v1.0 |
| Services | All services stabilized for PoC v1.0 |

### Implementation tasks

Refactor compose files and pin image versions.

Add health checks and startup waits.

Consolidate OpenAPI, Postman collection and scripts.

Run full end-to-end test from forecast to traceability.

Add troubleshooting, adopter README and architecture diagrams.

Create release v1.0 and repository landing page.

### Tutorial steps

1. make reset && make start.

2. make seed loads master data, stock, BoM and forecast.

3. make demo-e2e runs MPS, creates MO, reserves, schedules, executes, handles event, receives finished goods.

4. Query final MO, WorkOrders, stock, traceability and KPIs.

5. Run make test-e2e.

6. Publish v1.0 release notes.

Acceptance criterion: End-to-end demo produces one done MO, three done WorkOrders, consumed components, one finished lot, traceability and at least one KPI.

# 6. Final release checklist

| Checklist item | Required result |
| --- | --- |
| Docker runtime | make reset && make start runs successfully on a clean machine with Docker. |
| Tutorial coverage | Twelve tutorial folders with README, requests, seed data, expected outputs and tests. |
| Data model package | Every type has schema.json, README.md, doc/spec.md, example.jsonld and example-normalized.jsonld. |
| Context versions | v1.0 context file exists and latest points to v1.0. |
| OpenAPI | All business commands are documented with request, response and error examples. |
| Postman | Collection covers all tutorials and end-to-end demo. |
| CI | GitHub Actions validates schemas, starts stack and runs test-all. |
| Release notes | v1.0 release explains scope, limitations, known issues and next roadmap. |
| Adopter docs | Architecture document and adopter guide are linked from README. |
| License and governance | Open source license, contribution guidelines and issue templates are present. |

# 7. Example issue templates

# Tutorial increment issue

Title: Tutorial XX - <capability>

## Business value

## Models introduced or changed

## Services introduced or changed

## API endpoints

## Tutorial exercises

## Automated tests

## Acceptance criteria

# Model issue

Title: Model - <EntityType>

## Purpose

## Required properties

## Optional properties

## Relationships

## JSON Schema

## NGSI-LD examples

## Validation notes

# References

ETSI GS CIM 009 V1.9.1, Context Information Management (CIM); NGSI-LD API: https://www.etsi.org/deliver/etsi_gs/CIM/001_099/009/01.09.01_60/gs_CIM009v010901p.pdf

Official NGSI-LD website: https://ngsi-ld.org/

FIWARE tutorials.Step-by-Step GitHub repository: https://github.com/FIWARE/tutorials.Step-by-Step

FIWARE tutorials.NGSI-LD GitHub repository: https://github.com/FIWARE/tutorials.NGSI-LD

FIWARE Orion-LD Context Broker repository: https://github.com/FIWARE/context.Orion-LD

Smart Data Models guidelines: https://github.com/smart-data-models/data-models/blob/master/guidelines.md

Smart Data Models contribution manual: https://smartdatamodels.org/wp-content/uploads/2020/05/20200514-SINGLE-DATA-MODEL-CONTRIBUTION.pdf

Smart Data Models documentation structure: https://smart-data-models.github.io/data-models/